## Template
Foundation Inspection Checklist
Excavation, reinforcement and pour checks before concrete goes in and the work is buried. · Free template from SiteAudit — https://siteaudit.app/templates
Project |  | Location / grid ref |  | Foundation type |  | Drawing ref
Inspected by |  | Date |  | Weather |  | Building control notified
Ref | Item | Y / N / N/A | Observation / evidence | Action required | Owner | Due date | Status
1. Excavation
1 | Excavation set out to the correct position and dimensions
2 | Formation depth achieved and checked against the drawing
3 | Bearing stratum matches the ground investigation and is approved
4 | Excavation clean, dry and free of loose material and water
5 | Sides stable or supported; safe access provided
6 | Existing services and adjacent foundations identified and protected
2. Before the pour
7 | Formwork and shuttering in position, secure, plumb and clean
8 | Reinforcement type, size, spacing and laps as drawn
9 | Cover to reinforcement correct and spacers in place
10 | Starter bars, dowels and holding-down bolts positioned and secured
11 | Ducts, service entries and DPC provisions in place
12 | Building control or engineer inspection held and released in writing
3. Concrete
13 | Delivery ticket checked: mix, strength class, slump and time
14 | Slump or workability test carried out and recorded
15 | Test cubes taken, labelled and stored correctly
16 | Concrete placed without segregation and compacted properly
17 | Levels checked and surface finished as specified
4. After the pour
18 | Curing and protection in place (cold weather, hot weather, rain)
19 | Formwork strike times observed
20 | As-built levels and positions recorded
21 | Photographic record taken before backfilling
22 | Cube test results received and compliant

## How to use
Foundation Inspection Checklist — how to use it
1. | This is the highest-consequence inspection on most projects, because everything after it is buried and expensive to expose.
2. | Do not let the pour start until the reinforcement inspection is released in writing. A verbal release is worth nothing afterwards.
3. | Record the actual measurement for cover and spacing, not a tick. The number is what the engineer needs.
4. | Photograph the reinforcement from enough angles to identify the grid location later. Photographs of anonymous rebar prove nothing.
5. | Keep the delivery tickets with this sheet — mix, time and slump are the first things queried if cube results fail.
Tired of retyping this into a spreadsheet?
SiteAudit runs this checklist on your phone or tablet, works fully offline, attaches photos to every line and exports a signed PDF report before you leave site. Free to start — https://siteaudit.app