## Template
Construction Handover Checklist
Everything that has to be complete, tested, certified and handed over before practical completion. · Free template from SiteAudit — https://siteaudit.app/templates
Project |  | Address |  | Client |  | Contract
Practical completion date |  | Prepared by |  | Date
Ref | Item | Y / N / N/A | Observation / evidence | Action required | Owner | Due date | Status
1. Works complete
1 | All works complete in accordance with the contract documents
2 | Punch list and snagging items closed and verified
3 | Builder's clean completed to all areas
4 | Temporary works, site accommodation and protection removed
5 | External works, landscaping and making good complete
2. Testing & commissioning
6 | Mechanical systems commissioned and witnessed
7 | Electrical installation tested and certified
8 | Fire alarm and detection system tested and certified
9 | Emergency lighting tested and certified
10 | Water systems flushed, chlorinated and sampled
11 | Lifts, gates and powered doors commissioned and certified
3. Statutory certificates
12 | Building control completion certificate issued
13 | Electrical installation certificate (EIC) issued
14 | Gas safety certificate issued
15 | Fire risk assessment completed for the completed building
16 | Air tightness and energy performance certificates issued
4. Documentation
17 | As-built drawings issued in agreed format
18 | Operation and maintenance manuals issued and indexed
19 | Health and safety file complete and handed to the client
20 | Equipment schedules, warranties and guarantees collated
21 | Asset register and spares list provided
5. Access & training
22 | Keys, fobs and access codes handed over and recorded
23 | Alarm and access control codes reset and transferred
24 | Client and facilities team trained on plant and controls
25 | Emergency and out-of-hours contact list issued
26 | Utility accounts transferred to the client
6. Commercial
27 | Final account position agreed or recorded
28 | Retention and defects liability period confirmed in writing
29 | Insurances transferred to the client from the handover date
30 | Defects reporting procedure agreed and issued

## How to use
Construction Handover Checklist — how to use it
1. | Start filling this in at least six weeks before practical completion. Most of what delays handover is paperwork, not building work.
2. | Certificates are the long lead item — chase the ones that depend on third parties first.
3. | Do not accept "to follow" against a documentation line. Record the date it was actually received.
4. | Hand over the health and safety file as a condition of practical completion, not afterwards.
Tired of retyping this into a spreadsheet?
SiteAudit runs this checklist on your phone or tablet, works fully offline, attaches photos to every line and exports a signed PDF report before you leave site. Free to start — https://siteaudit.app