## Template
Construction Project Close-Out Checklist
Commercial, contractual and physical close-out steps after practical completion. · Free template from SiteAudit — https://siteaudit.app/templates
Project |  | Contract |  | Client |  | Practical completion date
Defects liability expiry |  | Prepared by |  | Date
Ref | Item | Y / N / N/A | Observation / evidence | Action required | Owner | Due date | Status
1. Physical close-out
1 | Site accommodation, plant and temporary works removed
2 | Temporary supplies disconnected and accounts closed
3 | Site fully cleared, cleaned and made good
4 | Surplus materials returned, transferred or disposed of
5 | Final photographic record of the completed works taken
2. Defects period
6 | Defects reporting procedure issued to the client
7 | Defects log opened and responsibility assigned
8 | Subcontractor obligations during the defects period confirmed in writing
9 | End-of-defects inspection scheduled before the liability period expires
10 | Retention release dates diarised
3. Commercial
11 | Final account agreed and signed
12 | All subcontractor final accounts settled
13 | Variations, claims and extensions of time closed out
14 | Retention position agreed and release triggered
15 | Outstanding invoices and credits reconciled
4. Documentation & records
16 | Health and safety file issued and receipt confirmed
17 | As-built information and O&M manuals delivered
18 | Warranties, guarantees and collateral warranties collected
19 | Project records archived to the retention policy
20 | Lessons learned recorded and shared with the team
5. People & closeout admin
21 | Site team demobilised and reassigned
22 | Access cards, keys and IT accounts recovered
23 | Insurances adjusted from the completion date
24 | Client feedback obtained and reference agreed

## How to use
Construction Project Close-Out Checklist — how to use it
1. | Close-out is where margin quietly disappears. Everything here has a cost attached to leaving it undone.
2. | Diarise the end-of-defects inspection the day practical completion is certified, not eleven months later.
3. | Do not demobilise the site team before the documentation is collected — nobody else knows where it is.
4. | Retention is the most commonly forgotten item on this list. Put the release dates in a calendar with an owner.
Tired of retyping this into a spreadsheet?
SiteAudit runs this checklist on your phone or tablet, works fully offline, attaches photos to every line and exports a signed PDF report before you leave site. Free to start — https://siteaudit.app