## Template
Quality Inspection Checklist
Trade-by-trade quality checks with hold points, tolerances and sign-off. · Free template from SiteAudit — https://siteaudit.app/templates
Project |  | Element / location |  | Trade / subcontractor |  | Specification ref
Inspected by |  | Date |  | ITP ref
Ref | Item | Y / N / N/A | Observation / evidence | Action required | Owner | Due date | Status
1. Before work starts
1 | Approved drawings and specification issued to the trade and current revision confirmed
2 | Materials delivered match the specification and approved samples
3 | Previous trade's work inspected, accepted and signed off
4 | Setting out checked against the drawing and datum
5 | Method statement and inspection and test plan agreed
2. Workmanship
6 | Work is within the tolerances stated in the specification
7 | Lines, levels and plumb checked and recorded
8 | Fixings are of the specified type, spacing and embedment
9 | Junctions, penetrations and terminations are as detailed
10 | Finish is consistent with the approved sample or benchmark
3. Hold & witness points
11 | Hold points released in writing before covering up
12 | Witness points attended by the client or consultant as required
13 | Records, test results and certificates obtained before proceeding
14 | Photographic record taken of work that will be concealed
4. Protection & completion
15 | Completed work protected from following trades
16 | Area left clean and free of debris and surplus material
17 | Defects raised, recorded and issued to the responsible trade
18 | Element signed off as complete and ready for the next trade

## How to use
Quality Inspection Checklist — how to use it
1. | Inspect before the work is covered up, not after. A hold point released retrospectively is not a hold point.
2. | Record the actual measurement, not just "within tolerance". The number is the evidence.
3. | Photograph everything that will be concealed — services in walls, waterproofing, reinforcement, fixings.
4. | If the previous trade's work is not acceptable, do not let the next trade start on top of it.
Tired of retyping this into a spreadsheet?
SiteAudit runs this checklist on your phone or tablet, works fully offline, attaches photos to every line and exports a signed PDF report before you leave site. Free to start — https://siteaudit.app